## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration (days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Select tablet vendor
1.1. Schedule initial project meeting |  | 2023-02-20 | 2023-02-21 | 1 | Alex | Completed | bar: WEEK 1 M to WEEK 1 T
1.2. Research tablet features |  | 2023-02-21 | 2023-02-23 | 3 | Sarah | Completed | bar: WEEK 1 T to WEEK 1 R
1.3. Test tablets |  | 2023-02-23 | 2023-02-28 | 5 | Kate | Completed | bar: WEEK 1 R to WEEK 2 T
1.4. Select the right tablet for the project |  | 2023-02-28 | 2023-03-03 | 3 | Dan | Completed | bar: WEEK 2 T to WEEK 2 F
1.5. Generate quotes and review costs |  | 2023-03-03 | 2023-03-10 | 7 | Alex | Completed | bar: WEEK 2 F to WEEK 3 F
1.6. Create contracts and statements of work for vendors |  | 2023-03-10 | 2023-03-15 | 5 | Alex | Completed | bar: WEEK 3 F to WEEK 4 W
Milestone 2: Install tablets
2.1. Receive shipment of tablets | 7 days + 4 days for shipping old devices | 2023-03-15 | 2023-03-25 | 11 | Brian | Completed | bar: WEEK 4 W to WEEK 5 F
2.2. Schedule an electrician |  | 2023-03-25 | 2023-04-01 | 7 | Alex | Completed | bar: WEEK 6 M to WEEK 6 F
2.3. Complete electrician wiring |  | 2023-04-01 | 2023-04-02 | 1 | Peter | Completed
2.4. Install tablets in the bar areas at the Downtown and North restaurant locations |  | 2023-04-02 | 2023-04-04 | 2 | Peter | Completed
2.5. Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 2023-04-04 | 2023-04-09 | 5 | Sarah | In Progress
2.6. Update POS by contacting FlatPlate |  | 2023-04-09 | 2023-04-13 | 4 | Ed | Not started
2.7. Sync tablet software with POS system |  | 2023-04-13 | 2023-04-13 09:36 | 0.4 | Ed | Not started
Milestone 3: Training and surveys
3.1. Get waitstaff buy-in for the tablet roll-out |  | 2023-04-13 | 2023-04-13 02:24 | 0.1 | Terry | Not started
3.2. Train management, FOH staff, and BOH staff |  | 2023-04-13 02:24 | 2023-04-14 02:24 | 1 | Sarah, Terry | Not started
3.3. Train the staff to update the menu |  | 2023-04-14 02:24 | 2023-04-14 12:00 | 0.4 | Sarah, Terry | Not started
3.4. Conduct test run after training staff with friends and family |  | 2023-04-14 12:00 | 2023-04-16 12:00 | 3 | Kate | Not started
3.5. Implement a post-dining survey to assess customer satisfaction |  | 2023-04-16 12:00 | 2023-04-19 12:00 | 3 | Alex | Not started
3.6. Message about launch date to stakeholders |  | 2023-04-19 12:00 | 2023-04-20 12:00 | 1 | Alex | Not started
Formulas:
Due Date = [Start Date]+[Duration (days)]
Due Date = [Start Date]+[Duration (days)]-1
Start Date = [Due Date, row above]

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Implement a post-dining survey to assess customer satisfaction |  | 3 |  |  |  | Medium
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 7 |  |  |  | Medium
Get waitstaff buy-in for the tablet roll-out |  | 0.1 |  |  |  | Low
Conduct test run after training staff with friends and family |  | 3 |  |  |  | High
Train waitstaff on how to use tablets |  | 0.4 |  |  |  | Medium
Train key staff members at each location for conducting employee trainings |  | 0.2 |  |  |  | Medium
Receive shipment of tablets | 7 days + 4 days for shipping old devices | 11 |  |  |  | High
Update POS by contacting FlatPlate |  | 4 |  |  |  | Low
Sync tablet software with POS system |  | 0.4 |  |  |  | Medium
Complete electrician wiring |  | 2 |  |  |  | Medium

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Best Uses for Tablets at Your Restaurant | https://www.business.com/articles/best-tablet-uses-restaurants/ | 2023-02-23
How to enhance service with tabletop tablets | https://www.restaurantbusinessonline.com/technology/how-enhance-service-tabletop-tablets | 2023-02-23
,

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Functionality | Average ticket time: 8 minutes for appetizers, 12-15 minutes for entrees. | Are customers receiving the correct order? | % of customers who use tablets receive the correct order | FALSE
Ease of Use | Quicker checkout: one minute checkout time | How quickly are customers learning how to navigate the tablets? | Waitstaff can log into their tablet accounts on the first try | FALSE
Customer Satisfaction | Increase customer retention in tablet areas by 5% | Are customers having a better dining experience with the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | FALSE
Functionality | 98% order accuracy | Do all the tablets work as expected? | Tablet error logs report a maximum of one error per shift | FALSE
Customer Satisfaction | Lobby wait time of under 10 minutes | Do customers feel like returning again? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time: 8 minutes for appetizers, 12-15 minutes for entrees. | Are customers receiving the correct order? | % of customers who use tablets receive the correct order | Were you able to place an order successfully? | Yes/No | Yes | No
Quicker checkout: one minute checkout time | How quickly are customers learning how to navigate the tablets? | Waitstaff can log into their tablet accounts on the first try | Did you wait for more than 30 minutes? | Yes/No | Yes | No
Increase customer retention in tablet areas by 5% | Are customers having a better dining experience with the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | Would you recommend the restaurant to your friends and family? | Scaled | 1 = Low | 2 | 3 | 4 | 5 = High
98% order accuracy | Do all the tablets work as expected? | Tablet error logs report a maximum of one error per shift | Would you visit the restaurant again? | Scaled | 1 = Low | 2 | 3 | 4 | 5 = High
Lobby wait time of under 10 minutes | Do customers feel like returning again? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | Did you use tablets on your last visit? | Yes/No | Yes | No
|  |  | Have you visited Sauce & Spoon previously? | Yes/No | Yes | No
|  |  | Did you face any technical issues with the tablet? | Yes/No | Yes | No
|  |  | How long was your dining experience? | Multiple choice | 1 hour | 2 hours | 3 hours | More than 3 hours
|  |  | Did you receive your order accurately? | Yes/No | Yes | No
|  |  | Was the tablet easy to navigate? | Scaled | 1 = Low | 2 | 3 | 4 | 5 = High
|  |  | Any feedback | Open-ended | Open-ended